## Decision Log
Artifact 10 — Decision & Assumption Log
Key portfolio decisions, rationale, impacts, and validation needs
This log preserves the reasoning behind the case study so reviewers can distinguish deliberate choices from verified facts.
Decision ID | Decision | Rationale | Impact | Evidence / Basis | Validation Needed? | Owner | Status
DEC-001 | Create a separate BA case-study repository rather than embedding all BA artifacts in the original analytics repository. | Separates technical implementation evidence from BA methodology while preserving a clear relationship between the two. | Creates a second portfolio project with cross-links to the Power BI solution. | Portfolio design decision | No | Chase Brangham | Accepted
DEC-002 | Treat the 90-day threshold as an analytical monitoring indicator, not an official service-level target. | The existing analytics project used 90+ days to describe aging, but no public evidence establishes it as a City SLA. | All requirements, UAT, and recommendations use careful wording around the threshold. | Existing project design + scope limitation | Yes, in real engagement | Chase Brangham | Accepted
DEC-003 | Reconstruct requirements retrospectively from the completed solution and public information. | The Power BI project already exists, so the BA package is intentionally a portfolio extension rather than a claim of pre-build elicitation. | Requirement status is labeled Reconstructed / Proposed instead of Approved. | Portfolio case-study disclosure | No | Chase Brangham | Accepted
DEC-004 | Model the As-Is workflow only at the level supported by public status/routing information. | Internal department procedures, work-order rules, staffing, and SLAs are not publicly available in the dataset. | Process map remains intentionally high level and includes a modeling note. | City FAQ + Open Data limitations | Yes, in real engagement | Chase Brangham | Accepted
DEC-005 | Use council district and service type as primary segmentation dimensions. | Both dimensions are available in the analytical project and directly support geographic/category workload questions. | Requirements and user stories explicitly cover district and service-type comparison. | Existing model and stakeholder-use assumptions | Yes, with stakeholders | Chase Brangham | Accepted
DEC-006 | Use the existing Power BI dashboard as the implemented solution for traceability. | Avoids inventing a hypothetical product and connects BA artifacts to a real portfolio deliverable. | RTM and UAT map directly to current report capabilities. | Completed Power BI project | No | Chase Brangham | Accepted
DEC-007 | Keep UAT cases in Planned status unless independently executed and evidenced. | Formal acceptance requires real execution and, ideally, representative users. | Prevents the portfolio from implying City approval or user sign-off. | Professional integrity / scope | No | Chase Brangham | Accepted
DEC-008 | Frame recommendations as investigation and prioritization signals rather than causal conclusions. | Public request data can reveal patterns but not reliably prove staffing, process, budget, or root-cause explanations. | Recommendations emphasize follow-up analysis and operational review. | Dataset scope limitation | No | Chase Brangham | Accepted
DEC-009 | Treat Referred as an inactive/workflow-exit status, not proof that the underlying physical issue was resolved. | Official City documentation states referred requests leave Get It Done visibility and may continue with an outside agency or disconnected City department. | Prevents referral metrics and dispositions from being overstated as completed maintenance outcomes. | City Open Data portal + Get It Done status guidance | No | Chase Brangham | Accepted
DEC-010 | Add a recruiter-facing master case study while retaining detailed artifacts as a second layer. | A reviewer should understand the project narrative without opening every workbook, while technical reviewers should still be able to inspect detailed evidence. | Creates a two-layer portfolio structure: narrative case study + artifact library. | Portfolio design review | No | Chase Brangham | Accepted

## Assumption Log
Assumption Log
Assumptions used to demonstrate BA methodology in the absence of internal stakeholder access
Assumptions should be validated or replaced with evidence in a real engagement.
Assumption ID | Assumption | Why Needed | Risk if Wrong | Validation Approach | Owner | Status
ASM-001 | Operations leadership, department/program managers, analysts, council district staff, intake staff, service-delivery teams, IT/data support, and residents are reasonable stakeholder groups for modeling purposes. | Needed to demonstrate stakeholder analysis without direct City interviews. | Requirements or engagement strategy could differ from actual organizational roles. | Validate organization chart and conduct stakeholder identification workshop. | Chase Brangham | Open
ASM-002 | The public fields and current Power BI model are sufficient to demonstrate backlog, aging, geographic, category, and throughput analysis. | Needed to define a bounded portfolio solution. | Important operational context may be absent from public data. | Compare with internal data dictionary and reporting needs in a real engagement. | Chase Brangham | Open
ASM-003 | The current Power BI solution can stand in as the implemented analytical solution for retrospective traceability. | Needed to connect reconstructed requirements to real solution evidence. | The dashboard may not reflect every requirement a real stakeholder would request. | Validate requirements before implementation in a real engagement. | Chase Brangham | Accepted for portfolio
ASM-004 | A 90-day aging threshold is useful as a monitoring cut for this analysis. | Needed to operationalize the existing backlog-aging finding. | It may not match service-type-specific expectations or official targets. | Validate service-level expectations by category and stakeholder. | Chase Brangham | Open
ASM-005 | Council district is a useful geographic management lens for at least some reviewers. | Needed to demonstrate geographic segmentation. | Operational ownership may follow department, asset, or service boundaries instead. | Validate decision-making geography with stakeholders. | Chase Brangham | Open
ASM-006 | Request-versus-disposition activity is a useful throughput indicator, while not being a complete operational performance measure. | Needed to interpret monthly flow without overstating causality. | Disposition timing or status semantics could differ by service type. | Validate definitions and work-order relationships with process owners. | Chase Brangham | Open
ASM-007 | Blank categorical values should remain visible as 'Unknown' rather than be silently excluded. | Needed for transparent data-quality handling. | Some blanks may have a specific business meaning that should use another label. | Validate data dictionary and source-system semantics. | Chase Brangham | Open
ASM-008 | The public status model (New, In Process, Closed, Referred) is sufficient for a portfolio-level workflow model, but not for internal work-order or department process analysis. | Needed to bound process modeling to public evidence. | Internal routing, scheduling, work-order, and closure behavior could vary by service type and department. | Validate internal process variants with process owners and system documentation in a real engagement. | Chase Brangham | Open

## Source Register
Source Register
Public sources used to ground the case-study context and process model
These sources support public facts only; project-specific findings come from the original analytics project.
Source | Use in Case Study | URL | Notes
City of San Diego — Get It Done | Service scope, online services, ability to check report status | https://www.sandiego.gov/get-it-done | Official City source
Get It Done FAQ — Performance & Analytics | Public status definitions (New, In Process, Closed) and routing/work-order context | https://getitdone.sandiego.gov/TSWCommunityFAQ | Official Get It Done FAQ
City of San Diego Open Data — Get It Done Reports | Public dataset scope, available open/closed files, and limitation that details of how each report was addressed are outside the dataset | https://data.sandiego.gov/datasets/get-it-done-reports/ | Official Open Data source
Get It Done Guidelines | Public guidance on choosing categories, routing, and appropriate use of Get It Done | https://www.sandiego.gov/sites/default/files/get-it-done-guidelines.pdf | Official City PDF
How to Get It Done on the New Mobile App | Public explanation of report status labels including Referred, used only as context for the exception path in the simplified As-Is map | https://www.sandiego.gov/get-it-done/how-to-get-it-done-on-the-new-mobile-app | Official City source
SRC-006 | City of San Diego Open Data Portal — Get It Done Reports | https://data.sandiego.gov/datasets/get-it-done-reports/ | Dataset scope, source files, field definitions, and limitations
SRC-007 | City of San Diego — Tips for working with Get It Done data | https://data.sandiego.gov/help/articles/tips-getitdone-311-requests/ | Status semantics: New/In Process active; Closed/Referred inactive; Referred exits Get It Done visibility
SRC-008 | City of San Diego — Get It Done status FAQ | https://getitdone.sandiego.gov/TSWCommunityFAQ | Public process/status definitions and routing/work-order descriptions
SRC-009 | Companion Power BI analytics repository | https://github.com/ChaseBrangham/san-diego-service-operations | Implemented analytical solution, architecture, measures, findings, and screenshots