## UAT Plan
Artifact 08 — UAT Plan & Test Cases
User Acceptance Testing design for the portfolio solution
This is a planned UAT artifact. No City user acceptance or formal production sign-off is claimed.
Plan Element | Definition | Portfolio Application | Status
Objective | Confirm that the solution satisfies documented business and functional requirements from a user perspective. | Validate the Power BI solution against reconstructed requirements and acceptance criteria. | Defined
Test Scope | Executive KPIs, backlog aging, district/service-type analysis, monthly throughput, filtering, data-quality handling, documentation/traceability. | Covers the capabilities mapped in the RTM; excludes internal City systems and production integrations. | Defined
Test Participants | Representative business users and BA/analyst roles in a real engagement. | Simulated personas only; no City personnel participated. | Simulated
Entry Criteria | Requirements baselined, solution available, test data accessible, expected results defined. | Portfolio requirements and current Power BI solution available. | Met for portfolio review
Exit Criteria | All Must-priority UAT cases executed; no unresolved critical defects; agreed acceptance decision documented. | Not executed with real stakeholders; remains a demonstration plan. | Not executed
Defect Handling | Log observed mismatch, severity, evidence, owner, and retest result. | Defect fields are included in the test-case sheet. | Defined
Evidence | Screenshots, filtered dashboard views, calculation reconciliation, or documentation references. | Would be attached during execution; evidence column is intentionally blank/planned. | Planned
Acceptance Authority | Business product/process owner or designated stakeholder in a real engagement. | Not applicable to this public portfolio case study. | Not applicable

## UAT Test Cases
UAT Test Cases
Business-facing scenarios mapped to requirements and user stories
All cases are marked Planned unless independently executed and evidenced. This avoids representing portfolio validation as formal stakeholder acceptance.
Test ID | Scenario | Business Goal | Mapped Requirements / Stories | Preconditions | Test Steps | Expected Result | Priority | Status | Actual Result / Evidence | Defect ID
UAT-01 | Validate total request KPI | Confirm top-level workload is represented correctly. | FR-02 / US-01 | Consolidated model loaded; known row-count reconciliation available. | 1) Open Executive Overview. 2) Clear filters. 3) Compare Total Requests KPI with reconciled model count. 4) Apply a supported filter and re-check. | KPI matches the modeled request count in the active filter context and updates when filters change. | Must | Planned
UAT-02 | Validate 90+ day open backlog | Confirm aging indicator includes only currently open requests meeting the portfolio threshold. | FR-03 / US-02 | Open requests contain request date/age fields and status. | 1) Identify known open records above and below 90 days. 2) Review KPI. 3) Apply a segment filter. 4) Reconcile count. | Backlog ≥90 Days counts only open records aged at least 90 days; filtered results reconcile to the same rule. | Must | Planned
UAT-03 | Validate council district comparison | Confirm users can identify geographic backlog concentration. | FR-04 / US-03 | Council district field available. | 1) Open district visual. 2) Compare district totals with grouped model output. 3) Select one district. | District values reconcile to the model and selecting a district updates applicable report context. | Must | Planned
UAT-04 | Validate service-type backlog | Confirm users can identify major service-category backlog drivers. | FR-05 / US-04 | Service type field available. | 1) Open service-type visual. 2) Compare leading categories with grouped model output. 3) Select a category. | Category totals reconcile to the model and largest contributors are visually identifiable. | Must | Planned
UAT-05 | Validate requests vs dispositions trend | Confirm monthly intake and completion activity can be compared consistently. | FR-06 / US-05 | Monthly request and disposition measures available. | 1) Open monthly trend. 2) Check selected months against model aggregates. 3) Apply a filter. | Both series use the same month/filter context and reconcile to model aggregates. | Must | Planned
UAT-06 | Validate net request flow calculation | Confirm net flow is calculated consistently as requests minus dispositions. | FR-07 / US-06 | Monthly request and disposition measures available. | 1) Select sample months. 2) Calculate requests minus dispositions independently. 3) Compare to report. | Net Request Flow equals Requests - Dispositions for each tested month/filter context. | Must | Planned
UAT-07 | Validate interactive filtering | Confirm dashboard interactions behave consistently. | FR-08; FR-09 / US-07 | Supported slicers/filters available. | 1) Apply one filter. 2) Apply two combined filters. 3) Clear filters. 4) Test a no-record context if available. | Applicable KPIs and visuals update consistently, combined filters are honored, and clearing filters restores the base view. | Must | Planned
UAT-08 | Validate 'Unknown' category handling | Confirm blank category values remain visible and interpretable. | FR-10 / US-09 | At least one blank category exists or transformation can be inspected. | 1) Review Power Query transformation. 2) Filter/group the transformed field. | Blank categorical values are labeled 'Unknown' and remain available for analysis. | Should | Planned
UAT-09 | Validate open vs completed distinction | Confirm backlog metrics are not conflated with historical completed volume. | FR-11 | Open and closed/disposition data are present. | 1) Compare backlog measures to open-record population. 2) Compare disposition measures to completed records. 3) Review definitions. | Backlog measures use open records; disposition/completion measures use their documented completed-record logic. | Must | Planned
UAT-10 | Validate executive-to-detail usability | Confirm reviewers can move from high-level signals to supporting analysis. | FR-12; NFR-01 / US-10 | Both report pages available. | 1) Open Executive Overview. 2) Identify key KPI and driver. 3) Open deeper analysis. 4) Locate supporting trend. | Core signals are understandable on the executive page and supporting detail is accessible without raw-data inspection. | Should | Planned
UAT-11 | Validate documentation and traceability | Confirm definitions, assumptions, limitations, and requirement links are discoverable. | NFR-02 / US-08 | Artifact package available. | 1) Pick a requirement. 2) Trace it through story, solution capability, and UAT. 3) Review assumptions and source notes. | The reviewer can trace the selected requirement end to end and distinguish public evidence from simulated assumptions. | Must | Planned
UAT-12 | Validate refresh/reproducibility approach | Confirm transformation logic can be repeated when source files are updated. | NFR-03 / US-09 | Power Query steps and source-file pattern documented. | 1) Review transformation steps. 2) Replace/update source file in a controlled copy. 3) Refresh model. 4) Check transformations. | Standardization and blank handling reapply consistently; measures remain available after refresh. | Should | Planned
UAT-13 | Validate duplicate reporting metrics | Confirm duplicate count/rate follow the documented parent-request rule and support segment analysis. | FR-13 / US-11 | Source data includes service_request_parent_id and duplicate measures are available. | 1) Identify sample records with and without a parent request. 2) Reconcile Duplicate Requests. 3) Recalculate Duplicate Rate. 4) Apply a service-type filter. | Duplicate count/rate match the documented parent-request logic and update consistently under supported filters. | Should | Planned
UAT-14 | Validate referral metrics and interpretation | Confirm referred records are counted consistently and not presented as confirmed physical resolutions. | FR-14; BR-09 / US-11 | Referred status exists and referral measures are available. | 1) Reconcile Referred Requests to records with status Referred. 2) Recalculate Referral Rate. 3) Review dashboard/documentation wording. 4) Apply a filter. | Referral metrics reconcile to the model, update with filter context, and documentation clearly states that referral is a workflow-exit status rather than proof of resolution. | Should | Planned